## Data
Migration Status — Source Data
Edit this sheet — other sheets update automatically. Status values: Green ¦ Yellow ¦ Red ¦ NA
SL No. | Pillar | Module Name | Tool Set | Migration Status | Status Label
1 | Ordering | Order Services | UFT | Red | Blocked
2 | Ordering | Ex-post | UFT | Red | Blocked
3 | Ordering | CBO_Ordering | Selenium | Green | Migrated
4 | Ordering | CMO_Ordering | Selenium | Green | Migrated
5 | Ordering | Robin | Selenium | Green | Migrated
6 | Ordering | OrderControl | Selenium | Yellow | In Progress
7 | Ordering | CuR | Selenium | Yellow | In Progress
8 | Ordering | E2E | Selenium | NA | Not Started
9 | Ordering | CuR New - Print Jobs | Selenium | NA | Not Started
10 | Ordering | CMO - New | Selenium | NA | Not Started
11 | Ordering | DT - Online Banking | Selenium | Red | Blocked
12 | Advisory | Advisory | Selenium | Green | Migrated
13 | Advisory | CoSMOS Services | UFT | Red | Blocked
14 | Advisory | Multiportfolio | Selenium | Green | Migrated
15 | Core | Admin Tool | UFT | Red | Blocked
16 | Core | Sanctions | Selenium | Green | Migrated
17 | Core | CMD | Selenium | Green | Migrated
18 | Core | ICCS | Selenium | Green | Migrated
19 | Core | Admin Tool - New (Core) | Selenium | NA | Not Started
20 | OIM | Decide | Tosca | Yellow | In Progress
21 | Unassigned | MarketDaten | UFT | Red | Blocked
22 | Unassigned | Smoke | Selenium | Yellow | In Progress
23 | Unassigned | HealthCheck | UFT | Red | Blocked
24 | Unassigned | EZS | — | NA | Not Started

## Colour Table
Migration Status — Colour-Coded View
● Migrated |  | ● In Progress |  | ● Blocked |  | ● Not Started
# | Pillar | Module Name | Tool | Status | Label
ORDERING
1 | Ordering | Order Services | UFT | Red | Blocked
2 | Ordering | Ex-post | UFT | Red | Blocked
3 | Ordering | CBO_Ordering | Selenium | Green | Migrated
4 | Ordering | CMO_Ordering | Selenium | Green | Migrated
5 | Ordering | Robin | Selenium | Green | Migrated
6 | Ordering | OrderControl | Selenium | Yellow | In Progress
7 | Ordering | CuR | Selenium | Yellow | In Progress
8 | Ordering | E2E | Selenium | NA | Not Started
9 | Ordering | CuR New - Print Jobs | Selenium | NA | Not Started
10 | Ordering | CMO - New | Selenium | NA | Not Started
11 | Ordering | DT - Online Banking | Selenium | Red | Blocked
ADVISORY
12 | Advisory | Advisory | Selenium | Green | Migrated
13 | Advisory | CoSMOS Services | UFT | Red | Blocked
14 | Advisory | Multiportfolio | Selenium | Green | Migrated
CORE
15 | Core | Admin Tool | UFT | Red | Blocked
16 | Core | Sanctions | Selenium | Green | Migrated
17 | Core | CMD | Selenium | Green | Migrated
18 | Core | ICCS | Selenium | Green | Migrated
19 | Core | Admin Tool - New (Core) | Selenium | NA | Not Started
OIM
20 | OIM | Decide | Tosca | Yellow | In Progress
UNASSIGNED
21 | Unassigned | MarketDaten | UFT | Red | Blocked
22 | Unassigned | Smoke | Selenium | Yellow | In Progress
23 | Unassigned | HealthCheck | UFT | Red | Blocked
24 | Unassigned | EZS | — | NA | Not Started

## Pillar Cards
Ordering — 11 modules |  |  | Advisory — 3 modules |  |  | Core — 5 modules
✔ 3 Migrated | ◑ 2 In Progress | ✕ 3 Blocked | ✔ 2 Migrated | ◑ 0 In Progress | ✕ 1 Blocked | ✔ 3 Migrated | ◑ 0 In Progress | ✕ 1 Blocked
○ 3 Not Started |  |  | ○ 0 Not Started |  |  | ○ 1 Not Started
Module | Tool | Status | Module | Tool | Status | Module | Tool | Status
Order Services | UFT | Blocked | Advisory | Selenium | Migrated | Admin Tool | UFT | Blocked
Ex-post | UFT | Blocked | CoSMOS Services | UFT | Blocked | Sanctions | Selenium | Migrated
CBO_Ordering | Selenium | Migrated | Multiportfolio | Selenium | Migrated | CMD | Selenium | Migrated
CMO_Ordering | Selenium | Migrated |  |  |  | ICCS | Selenium | Migrated
Robin | Selenium | Migrated |  |  |  | Admin Tool - New (Core) | Selenium | Not Started
OrderControl | Selenium | In Progress
CuR | Selenium | In Progress
E2E | Selenium | Not Started
CuR New - Print Jobs | Selenium | Not Started
CMO - New | Selenium | Not Started
OIM — 1 modules |  |  | Unassigned — 4 modules
✔ 0 Migrated | ◑ 1 In Progress | ✕ 0 Blocked | ✔ 0 Migrated | ◑ 1 In Progress | ✕ 2 Blocked
○ 0 Not Started |  |  | ○ 1 Not Started
Module | Tool | Status | Module | Tool | Status
Decide | Tosca | In Progress | MarketDaten | UFT | Blocked
|  |  | Smoke | Selenium | In Progress
|  |  | HealthCheck | UFT | Blocked
|  |  | EZS | — | Not Started

## Summary Dashboard
Migration Status — Summary Dashboard
24 |  | 8 |  | 7 |  | 4 | 5
Total Modules |  | Migrated |  | Blocked |  | In Progress | Not Started
Status by Pillar
Pillar | Total | Migrated | In Progress | Blocked | Not Started | % Done
Ordering | 11 | 3 | 2 | 3 | 3 | 27%
Advisory | 3 | 2 | 0 | 1 | 0 | 67%
Core | 5 | 3 | 0 | 1 | 1 | 60%
OIM | 1 | 0 | 1 | 0 | 0 | 0%
Unassigned | 4 | 0 | 1 | 2 | 1 | 0%

## Status Tracker
Module Status Tracker
Module Name | Pillar | Tool Set | Migration Status | Progress
Order Services | Ordering | UFT | Blocked | ░░░░░░░░░░ 0%
Ex-post | Ordering | UFT | Blocked | ░░░░░░░░░░ 0%
CBO_Ordering | Ordering | Selenium | Migrated | ██████████ 100%
CMO_Ordering | Ordering | Selenium | Migrated | ██████████ 100%
Robin | Ordering | Selenium | Migrated | ██████████ 100%
OrderControl | Ordering | Selenium | In Progress | █████░░░░░ 50%
CuR | Ordering | Selenium | In Progress | █████░░░░░ 50%
E2E | Ordering | Selenium | Not Started | ░░░░░░░░░░ 0%
CuR New - Print Jobs | Ordering | Selenium | Not Started | ░░░░░░░░░░ 0%
CMO - New | Ordering | Selenium | Not Started | ░░░░░░░░░░ 0%
DT - Online Banking | Ordering | Selenium | Blocked | ░░░░░░░░░░ 0%
Advisory | Advisory | Selenium | Migrated | ██████████ 100%
CoSMOS Services | Advisory | UFT | Blocked | ░░░░░░░░░░ 0%
Multiportfolio | Advisory | Selenium | Migrated | ██████████ 100%
Admin Tool | Core | UFT | Blocked | ░░░░░░░░░░ 0%
Sanctions | Core | Selenium | Migrated | ██████████ 100%
CMD | Core | Selenium | Migrated | ██████████ 100%
ICCS | Core | Selenium | Migrated | ██████████ 100%
Admin Tool - New (Core) | Core | Selenium | Not Started | ░░░░░░░░░░ 0%
Decide | OIM | Tosca | In Progress | █████░░░░░ 50%
MarketDaten | Unassigned | UFT | Blocked | ░░░░░░░░░░ 0%
Smoke | Unassigned | Selenium | In Progress | █████░░░░░ 50%
HealthCheck | Unassigned | UFT | Blocked | ░░░░░░░░░░ 0%
EZS | Unassigned | — | Not Started | ░░░░░░░░░░ 0%